## Sheet1
Task | Status | Kyle approval | Milestone | Task Type
Spreadsheet tracking completion of features/requirements with automatic score calculation. | Completed | TRUE | Milestone 1 | Basic |  | TOTAL MARKS | My marks | Kyle marks
Two self-imposed milestone Wednesdays with mapped features for each demonstration session. | Completed | TRUE | Milestone 1 | Basic | Basic | 13 | 10 | 10
Mermaid Diagram showing the functional layout of the planned codebase. | Completed | TRUE | Milestone 1 | Basic | Intermediate | 22 | 18 | 18
Coolant system with flow rate variable and pump speed slider control (0–100%). | Completed | TRUE | Milestone 1 | Basic | Advanced | 15 | 12 | 12
Control rod position slider (0–100%) that directly affects heat | Completed | TRUE | Milestone 1 | Basic | Total | 50 | 40 | 40
Reactor core temperature display in Celsius (with basic indications of safe operating threshold). | Completed | TRUE | Milestone 1 | Basic | MAX |  | 50 | 50
Turbine RPM display (0-3000 RPM) | Completed | TRUE | Milestone 1 | Basic
Generator electrical power output 8 segment display showing megawatts electrical (max 1000MWe) produced | Completed | TRUE | Milestone 1 | Basic
Basic loss condition: Reactor meltdown occurs when core temperature exceeds 800°C or Reactor explodes if pressure hits 20 MPa | Completed | TRUE | Milestone 1 | Intermediate
Score system: Score increases when within (0-100MWe) to the target power ouput, increase scales with accuracy | In progress | FALSE | Milestone 1 | Basic
SCRAM button shuts off reactor by setting control rods to 100% insertion (ends game to avoid catastrophy) | Not started | FALSE | Milestone 1 | Basic
Reset button that restarts simulation | Not started | FALSE | Milestone 1 | Basic
Display current reactor pressure | Completed | TRUE | Milestone 2 | Basic
Game timer displayed as MM:SS format that starts when reactor power exceeds 100 MW and stops on win/loss conditions. | Completed | TRUE | Milestone 1 | Basic
Use of a stylized 8 segment display for output | Completed | TRUE | Milestone 2 | Intermediate
Post-game statistics screen showing detailed (Choose some of the following) session breakdown: total time, revenue earned, highest temperature reached, average power output | Completed | TRUE | Final Due Date | Advanced
Sound effects package including: control interaction clicks, continuous reactor hum (pitch varies with power), alarm beeps (slow for yellow warning, rapid for red danger), SCRAM button clunk, grid demand change chime, and event notification sound. | Not started | FALSE | Final Due Date | Advanced
Change all displays to use Analog-style gauge or dial style displays, this includes making a display class | Completed | TRUE | Milestone 2 | Advanced
Instrument abstract class which has basic functionality of UI elements that are interactable or display only | Completed | TRUE | Milestone 1 | Advanced
Scene Management + Intro sequence | Completed | TRUE | Final Due Date | Advanced
Revenue Tracking (power output relative to grid demand) | Completed | TRUE | Final Due Date | Intermediate
Heat Transfer modelling via flow rate and temp difference | Completed | TRUE | Milestone 2 | Intermediate
Pressure modelling via reactor temp and control rod position | Completed | TRUE | Milestone 2 | Intermediate
Pressure release valve when held rapidly reduces pressure, but wastes coolant | Not started | FALSE | Milestone 2 | Intermediate
Responsiveness for web builds | In progress | FALSE | Milestone 2 | Intermediate
ReactorManager passes data around the classes it manages | Completed | TRUE | Milestone 2 | Intermediate
Arcitecture Planning and placeholder implementation of the reactor itself | Completed | TRUE | Milestone 1 | Intermediate
Arcitecture planning and placeholder classes for game managers | Completed | TRUE | Milestone 1 | Intermediate
Arcitecture planning and placeholder classes for the displays/buttons | Completed | TRUE | Milestone 1 | Intermediate